## PlanningTask_FOC_BLDC
BLDC_TiC2000_PROJECT
Process Scheduler: 10 weeks Start: 10-Mar -Finish:
|  | Team Members | TaiND |  | NhanMH
Document Folder:
STAGE | STAGE ID | TASK | DURATION (week) | RESPONSIBLE | SUB-TASK | OUTPUT | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
[7 empty] | 10/3 - 16/3 | 17/3 - 23/3 | 24/3-30/3 | 31/3 - 6/4 | 7/4 - 13/4 | 14/4 - 20/4 | 21/4 - 27/4 | 28/4 - 4/5 | 5/5-11/5 | 12/5 - 18/5
Stage 0: Kick off | 0 | Making working plan | 0 |  | - Implementation plan - Deadlines - Report | Working plan
Stage 1 : Project survey | 1.1 | Project target | 1 |  |  | Survey report
| 1.2 | MATLAB example project
| 1.3 | BLDC Control algorithm overview (FOC)
| 1.4 | Hardware + Software needed
Stage 2: Simulation | 2.1 | Run + Analyze example | 3 |  |  | Simulation report
2.2
2.3
2.4
Stage 3: Implement | 3.1 | Consider close or open loop control | 3 |  |  | Setup report + Complete model
| 3.2 | Set up gen-code program
| 3.3 | Hardware survey (Motor + Driver)
| 3.4 | Design wiring diagram
| 3.5 | Setup model
Stage 4: Experiment | 4.1 | Do experiment | 3 |  |  | Final report
| 4.2 | Analyze
| 4.3 | Writing final report | 1
UPDATE STATUS WORKLOAD
| Name |  | Day

## Sheet1 (hidden)
Phase | Task | Duration (week) | Responsible | Sub-tasks | Output
Phase 1 : System setup |  | 2
| battery check |  | Thịnh
| check wiring |  | Duy (cơ khí)
| check power supply for boards, sensors |  | Khoa, Minh
| Check current sense |  | Tuấn
| Dyno setup |  | Đại, Duy, Khoa, Minh
| Dyno testing |  | Bảo
| Design wheel speed sensing disc |  | Liêm
| Esp_now demo |  | Tuấn
| Review simulation program |  | Tài, Thịnh
Phase 2: System design |  | 1
| Design a new controller on Simulation |  | Thịnh
| Design system block diagram for experiment |  | Tuấn, Bảo
Phase 3: Implement |  | 1
| Implement hardware |  | Khoa, Tuấn
| Implement controller |  | Bảo, Tuấn
| Experimental setup planning |  | Thịnh
Phase 4: Experiment |  | 1
| Do experiment |  | Thịnh
| Analys |  | Thịnh
| Writing final report |  | Thịnh
5